## README
Risk Register — Miloshevski Health Partners (Fictional Company)
Portfolio project by Nikola Miloshevski Methodology: NIST SP 800-30 Rev. 1
This workbook is a sample enterprise risk register built for a fictional mid-size healthcare provider, Miloshevski Health Partners (~450 employees, 6 clinic locations, one EHR platform, cloud-hosted patient portal). It demonstrates how to identify, assess, score, and track information security risks using a NIST 800-30-aligned qualitative risk assessment methodology.
How this workbook is organized
• README — This page.
• Methodology — How likelihood, impact, and risk level are defined and scored (NIST 800-30 approach).
• Risk Register — The core deliverable — 15 identified risks, scored and tracked with owners and treatment plans.
• Risk Matrix — A 5x5 heat map visualizing where each risk falls by likelihood and impact.
Note on assumptions
Miloshevski Health Partners and all associated systems, incidents, and figures are fictional and were created for demonstration purposes. Likelihood and impact ratings reflect reasonable professional judgment for a healthcare organization of this size, not real incident data. Where a real framework or standard is referenced (NIST 800-30, NIST CSF, HIPAA Security Rule), the reference itself is real.

## Methodology
Risk Assessment Methodology
Based on NIST Special Publication 800-30 Rev. 1, "Guide for Conducting Risk Assessments." Risk is assessed qualitatively as a function of the likelihood of a threat event occurring and the impact if it does:
Risk Score = Likelihood (1–5) × Impact (1–5)
Likelihood Scale
Rating | Definition
1 — Rare | May occur only in exceptional circumstances (<5% chance within 1 year).
2 — Unlikely | Could occur at some point (5–25% chance within 1 year).
3 — Possible | Might occur at some point (25–50% chance within 1 year).
4 — Likely | Will probably occur in most circumstances (50–75% chance within 1 year).
5 — Almost Certain | Expected to occur in most circumstances (>75% chance within 1 year).
Impact Scale
Rating | Definition
1 — Negligible | Minimal disruption; no PHI exposure; no regulatory notification required.
2 — Minor | Limited disruption to one system/department; no PHI exposure.
3 — Moderate | Disruption to a business process; possible small-scale PHI exposure (<500 records).
4 — Major | Significant operational disruption; PHI breach affecting 500+ records; HHS/OCR notification required; media attention likely.
5 — Severe | Organization-wide outage or large-scale PHI breach; regulatory fines, litigation, and lasting reputational damage.
Risk Level Thresholds (Score = Likelihood × Impact)
Score Range | Risk Level & Required Action
1 – 4 | LOW — Accept and monitor; reassess annually.
5 – 9 | MEDIUM — Mitigate on a planned basis; reassess semi-annually.
10 – 15 | HIGH — Mitigate promptly; assign owner and target date; reassess quarterly.
16 – 25 | CRITICAL — Immediate action required; escalate to leadership.

## Risk Register
Miloshevski Health Partners — Information Security Risk Register
Risk ID | Date Identified | Asset / System | Threat Source | Threat Event | Vulnerability | Existing Controls | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Treatment Strategy | Recommended Action | Risk Owner | Target Date | Status
R-001 | 2026-01-15 | EHR Platform | External Threat Actor | Ransomware attack encrypts EHR database | Unpatched RDP server exposed to internet | EDR on endpoints; nightly backups | 4 | 5 | 20 | Critical | Mitigate | Disable public RDP; enforce MFA + VPN for remote access; test backup restoration | IT Security Manager | 2026-03-01 | In Progress
R-002 | 2026-01-15 | Employee Email | External Threat Actor | Phishing leads to credential compromise | No email banner for external senders; inconsistent phishing training | Spam filter; annual security awareness training | 4 | 4 | 16 | Critical | Mitigate | Deploy phishing-simulation program quarterly; enable external-sender email banners | Security Awareness Lead | 2026-04-01 | Not Started
R-003 | 2026-01-20 | Patient Portal (Cloud) | External Threat Actor | Cloud storage bucket misconfigured to public access | No automated cloud security posture scanning | Manual quarterly cloud config review | 3 | 5 | 15 | High | Mitigate | Implement CSPM tool for continuous cloud configuration monitoring | Cloud Infrastructure Lead | 2026-03-15 | In Progress
R-004 | 2026-01-20 | Third-Party Billing Vendor | Supply Chain | Vendor suffers data breach exposing shared patient billing data | No standardized vendor security assessment process | Signed BAA on file | 3 | 4 | 12 | High | Mitigate | Establish vendor risk assessment questionnaire; require SOC 2 report annually | Compliance Officer | 2026-05-01 | Not Started
R-005 | 2026-01-22 | Employee Laptops | Insider (Accidental) | Unencrypted laptop lost or stolen containing PHI | Not all endpoints have full-disk encryption enforced | MDM deployed on 80% of devices | 3 | 4 | 12 | High | Mitigate | Enforce full-disk encryption via MDM policy on 100% of endpoints | IT Operations Manager | 2026-02-28 | In Progress
R-006 | 2026-01-25 | Domain / Active Directory | External Threat Actor | Privilege escalation via weak admin password | Shared local admin credentials across workstations | Password complexity policy | 3 | 5 | 15 | High | Mitigate | Deploy LAPS for unique local admin passwords; enforce MFA on all admin accounts | IT Security Manager | 2026-03-01 | Not Started
R-007 | 2026-01-25 | All Systems | Insider (Malicious) | Departing employee retains access and exfiltrates data | Offboarding checklist not consistently followed | HR notifies IT on termination | 2 | 4 | 8 | Medium | Mitigate | Automate account deprovisioning tied to HRIS termination trigger | IT Operations Manager | 2026-04-15 | Not Started
R-008 | 2026-02-01 | Network Perimeter | External Threat Actor | DDoS attack disrupts patient portal availability | No DDoS mitigation service in place | Basic firewall rate limiting | 2 | 3 | 6 | Medium | Accept | Monitor; revisit if portal traffic or attack trends increase | Network Engineer | 2026-06-01 | Not Started
R-009 | 2026-02-01 | EHR Platform | Environmental | Unpatched critical vulnerability exploited (CVE backlog) | Patch cadence exceeds 90 days for non-critical systems | Monthly patch cycle for critical systems | 3 | 4 | 12 | High | Mitigate | Reduce patch SLA to 30 days for high/critical CVEs; adopt automated patch management tool | IT Security Manager | 2026-04-01 | Not Started
R-010 | 2026-02-05 | Data Backups | Environmental | Backup failure discovered only during a real recovery event | Backups not regularly test-restored | Nightly automated backups to offsite storage | 2 | 5 | 10 | High | Mitigate | Implement quarterly backup restoration test with documented results | IT Operations Manager | 2026-03-01 | In Progress
R-011 | 2026-02-10 | Clinic Facilities | Insider (Accidental) | Unauthorized physical access to server closet | Server closet lock shared among staff, not badge-controlled | Locked door, no badge access | 2 | 3 | 6 | Medium | Mitigate | Install badge-access control and access logging on all server closets | Facilities Manager | 2026-05-15 | Not Started
R-012 | 2026-02-10 | Remote Access (VPN) | External Threat Actor | Account takeover due to lack of MFA on VPN | MFA not enforced for all remote users | VPN with username/password only | 4 | 4 | 16 | Critical | Mitigate | Enforce MFA for all VPN connections org-wide | IT Security Manager | 2026-02-28 | In Progress
R-013 | 2026-02-12 | Medical Devices (IoT) | External Threat Actor | Legacy medical device with unsupported OS exploited as network pivot | Devices not network-segmented from clinical/admin network | Vendor-managed devices, limited visibility | 3 | 4 | 12 | High | Mitigate | Segment IoT/medical devices onto isolated VLAN with restricted access | Network Engineer | 2026-06-01 | Not Started
R-014 | 2026-02-15 | Compliance Program | Regulatory | Failure to complete annual HIPAA risk assessment on schedule | No formal recurring calendar/owner assigned | Risk assessment performed ad hoc | 2 | 4 | 8 | Medium | Mitigate | Assign compliance calendar with recurring annual HIPAA risk assessment owner | Compliance Officer | 2026-03-01 | In Progress
R-015 | 2026-02-15 | Social Media / Public Web | External Threat Actor | Business email compromise via executive impersonation (BEC) | No secondary verification process for wire/payment change requests | Standard email spam filtering | 3 | 4 | 12 | High | Mitigate | Require verbal callback verification for any payment or banking detail changes | Finance Director | 2026-03-15 | Not Started

## Risk Matrix
Risk Heat Map — Likelihood x Impact
Likelihood ↓ / Impact →
| L | 1 - Negligible | 2 - Minor | 3 - Moderate | 4 - Major | 5 - Severe
| 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 R-002,R-012 | 20 R-001
| 3 | 3 | 6 | 9 | 12 R-004,R-005,R-009,R-013,R-015 | 15 R-003,R-006
| 2 | 2 | 4 | 6 R-008,R-011 | 8 R-007,R-014 | 10 R-010
| 1 | 1 | 2 | 3 | 4 | 5
| Legend: | Low (1-4) | Medium (5-9) | High (10-15) | Critical (16-25)
Each cell shows Risk Score (Likelihood x Impact) and the Risk ID(s) that fall in that cell. See 'Risk Register' tab for full detail on each risk.